## Sayfa1
| 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31
DETERMINATION
subject research | bar: 2018-10-01
project determination | bar: 2018-10-08
decide to project scope | bar: 2018-10-15
CODE
Clinic
Customer Module
interface design | 2018-10-22: CEREN
list of customer | 2018-10-22: EGEHAN
add/delete customer
pet list of customer
add/delete pet
appointments | 2018-10-22: ESRA
sms sending
Pet Module
interface design | 2018-11-12: CEREN
pet registration info | 2018-11-12: EGEHAN
threatment record
vaccine record
sample analysis | 2018-11-12: ESRA
medical examination notes
Mobile
interface design | 2018-10-22: MERVE
login/registration | 2018-10-22: EREN
list of pets
threatment history
vaccine history
ask veterinary | 2018-11-12: MERVE
request appointment
appointment notification
PetCard
pet-id information | 2018-12-03: EREN
characteristic
health history
owner information | 2018-12-03: MEHMET
veterinary information
card scanner | 2018-12-03: EGEHAN
TEST
test | 2018-10-22: MEHMET
PRESENTATION | bar: 2018-12-31